# Milestone Summary Table

| Milestone | Planed Completion Date | Verification Method |
| --- | --- | --- |
| Project Proposal Presentation | 2-Sep | Presentation Given In class |
| Steady State comparison | 28-Sep | Results are within 20% difference from existing EES model |
| Transient Comparison | 26-Oct | Results are within 20% difference from existing component curve fit model |
| Uniting Generator & Absorber | 2-Nov | Results are within 20% difference from existing Cycle curve fit model |
| Final Report | 7-Nov | Report Submitted |
| Final Presentation | 2-Nov | Presentation Given In class |

# Git Hub Link

Link

# Gannt Chart Source File Link

Link